## Goals
| Project Summary | Indicators | Means of Verification | Risks/Assumptions
1.Goal Mission Statement
1.1 | Enable and empower marginalized communities to fully realize their capabilities and take charge of their own livelihoods and economic future through the implementation of Community Currency | Increased amount of trade in small scale businesses | Collection of baseline data and comparison with regular control surveys. Trade data assessment. | Adequate support from local authorities and adequate information collection
|  | Increased community based project that address needs identified by the users | Number of events/social actions occurred during the year | Stable political climate and active member participation
2. Outcome
2.1 | Have a self sustainable program running after 1 year after having shown significant economic, social and environmental, impacts | Trade volume increase in businesses | Comparison of baseline surveys with follow-up waves | Adequate support from local authorities, typical economic climate, expected community acceptance, understanding and use of the credit system
Sales increase in the businesses
Increase in market resilience
Increased sense of community belonging
|  | Increase in local events/social actions | Videos, photos, activity reports, blog entries
3. Outputs
3.1 | Build and maintain the capacity of the Social Enterprise (Community Currency backing) shop/business to a point where it is able to back the amount of voucher credit circulating inside the community and is profitable in itself | Amount of stock | Reports | Adequate personnel management
|  | Staff and office space is covered by the business | Reports and staff contracts | Adequate local support and personnel
3.2 | Creation of business network (local businesses, schools, youth groups, fishermen) and community usage and ownership of the Community Currency system | A legally registered Network exists which is trained and has the capacity to manage the program long term | Legal documents, membership lists, reports | Community capacity to monitor and manage the system
|  | Complementary currency voucher created and distributed | Reports, membership lists | Community understanding of how the program works
|  | Businesses experience growth in trade volume, sales, and stability | Trade data collected, analyzed and reported | Profitability for participation
3.3 | Development of community based commons projects | Number of events and participants | Videos and photo documentation of service work. Attendance sheets. Evaluation from participants. Data collected and reported. | Good community awareness, participation, involvement. Interest for promoting and developing activities from members and non-members
Amount of credit used at events
Impact of events (eg. waste collected,amount of food served, people perception changes)

## LogFrame
Logical Framework Community Currency (CC)
| Activity Title | Project Summary | Indicators | Means of Verification | Risks/Assumptions
4. Activities
Phase1 | Consultation | Baseline, Stakeholders, Community Support, Planning
1.1 | Pre-Baseline | Pre baseline. Initial consultation with community to talk with them through the plan and to be able to adjust the survey to their needs and contexts. Before baseline we need an financial and political audit | Meeting space provided by community, political and financial audit | Documented consent of community, attendance sheets, meeting minutes | Community leaders are interested in the project; Selecting local project leaders meets with little conflict
1.2 | Baseline | Baseline. Carrying out the survey for the calculation of the significant sample | Qualitative and quantitative data collection. Significant sample size and control groups | Reports, viewable data, gps coordinates, maps and photos | Community members are willing to participate with honesty in the survey taking process
1.4 | Post-Baseline | Post baseline (1) Analysis of results | Assess current levels of cooperation and trust in the proposed network
Assess capacity of stakeholder assets, businesses and network
|  | Post baseline (2) Feedback with the community. | Meeting space provided by community | Reports, plan, community attendance sheets, meeting minutes, (community partners) | Community continues to show interest in the project
Legal due-diligence
Focus group trainings
Develop long term plan with stakeholders
1.5 | Pre-Phase 2 test | Phase 1 test | Community is in full cooperation with good planning documents, partners and roles | Reports, signatures | Community is in full cooperation with good planning documents, partners and roles
Phase 2 | Development | Social Enterprise (SE) Development and Training
2.1 | Pre-investment | Developing business plans and performing audits and getting quotations on any proposed investment | Audit and business planning, quotations | Reports, spreadsheets | The business has the capability of growing and there is an external and local market for its goods and/or services
Amount of stock
Business profitability projection
2.2 | Social Enterprise Investment | Investment with conditions - cooperation of community - not owned by GE, acceptance of SC, community funding. | Signed contract with Social Enterprise - MOU | Legal contracts, receipts | The business has the capability of growing and there is an external and local market for its goods and/or services
Items purchased
Cash transferred
2.2 | Social Enterprise Capacity building | Training new or existing staff of the backing business on accounting and Community Currency usage. Capacity building of the backing business - bring in expertise and supply chain support | Training completion certification - 3rd party involvement on standards | Reports | Staff correctly understands their role and how the Community Currency works
2.3 | Pre-Phase 3 test | Phase 2 test - Products are being sold locally, and the social enterprise is integrated with community, and sustainable | Audit - Assets (stocking and turnover) can cover the entire amount of Community Currency planned to be put into circulation over a 6 month period. | Audit on assets and systems | The backing assets are well able to sell goods or services to the community using Community Currency
Phase 3 | Pilot | Community Currency Pilot
3.1 | Pre-Pilot | Pre Launch of pilot. Selection/training of a small solid pilot group (based upon the backing capacity of the business and amount desired to issue per person) | Number of users | Registration formats | People willing to begin as part of a smaller trading group
|  |  | Level of comprehension on how the system works | Community Currency usage training quizzes
3.2 | Pilot-Launch | (Test Launch) - Handing out vouchers with the support of local authorities | # voucher put into circulation | receipts
|  |  | Number of registration forms signed by network users and amount issued | Photos & video | Community is interested and motivated about CC
|  |  | Directory Created | Directory
|  |  | The number of public and local leaders that actively participate | Reports and partnerships | Civic leaders will cooperate
3.3 | Post-Pilot | Inline surveys to monitor economic, social and environmental impacts | Evidence of usage | Individual monitoring surveys (ODK) and in depth interviews, audit on biz and CCs | Community is interested and motivated about CC
Social Enterprise usage of CC
|  | Community driven activities (Frequency depending upon community. eg.monthly) | Reports, community attendance sheets, event minutes, photos
Number of branding and marketing events
|  | Evaluation of social enterprise currency redistribution mechanisms | SE books
|  | Feedback on pilot with community | # ODK surveys
Reporting to community
3.4 | Pre-Phase 4 test | Is the Social Enterprise able to accept more CC? Will they be able to accept all CC in circulation within a 1 year period? Average daily/weekly acceptance and usage - match with long term projection (amount issued vs amount accepted and used) | Business records and projections | Audit on assets and systems | The backing assets are well able to sell goods or services to the community using Community Currency
|  | Pilot groups are working well and understand the program, room for growth | Good usage, demand for more members/CC, Social Enterprise is accepting and reissuing | Audit on assets and systems | There is a risk that the pilot doesnt work for a particular community
Phase 4 | Launch | Community Currency Launch
4.1 | Pre-Launch | Pre registration of users | Number of users | Registration formats | People willing to join
|  | Contacting media | Number of media outlets contacted | Articles and stories written and published | Media will be interested
|  | Getting support of local authorities | Support letters from local authorities | Support letters from local authorities | Local authorities will be supportive
|  | Getting a venue | Venue is located and booked
|  | Marketing/Advertisement | Amount of marketing and advertisements done
4.2 | Launch | Official Launch event - Handing out vouchers with the support of local authorities | # voucher put into circulation | Voucher receipt records
|  |  | Number of registration forms signed by network users and amount issued | Photos & video
Directory Created
|  |  | The number of public and local leaders that actively participate | reports
4.3 | Post-Launch | Inline surveys to monitor economic, social and environmental impacts | Evidence of usage | Individual monitoring surveys (ODK) and in depth interviews, audit on biz and CCs | Community continues to show interest in the project
Social Enterprise usage of CC
|  | Community driven activities (Frequency depending upon community. eg.monthly) | Reports, community attendance sheets, event minutes, photos
Number of branding and marketing events
|  | Evaluation of social enterprise currency redistribution mechanisms | SE books
|  | Feedback on pilot with community | # ODK surveys
Reporting to community
4.4 | Pre-Phase 5 test | Is the Social Enterprise able to accept CC Sustainably | Business records and projections | Audit on assets and systems | The backing assets are well able to sell goods or services to the community using Community Currency
|  | Circulation is going well and people understand the program, at a good capacity (projecting out 1 years) | Good usage, demand for more members/CC, Social Enterprise is accepting and reissuing | Audit on assets and systems
Phase 5 | Proof of Work | Long term monitoring - proof of work/ impact / renewals / adjustments
5.1 | Quarterly Updates | 1st year post launch only | Good SC usage and SE operations | Reporting
5.2 | Pre-Endline | Pre Endline. consultation with community to talk with them through the plan and to be able to adjust the survey to their needs and contexts* | Meeting space provided by community | Documented consent of community, attendance sheets, meeting minutes | Community leaders are interested in the project; Selecting local project leaders meets with little conflict
5.3 | Endline | Endline. Carrying out the survey for the calculation of the significant impacts | Qualitative and quantitative data collection. Significant sample size and control groups | Reports, viewable data, gps coordinates, maps and photos | Community members are willing to participate with honesty in the survey taking process
5.4 | Post-Endline | Post Endline(1) Analysis of results | Assess current levels of cooperation and trust in the proposed network
Assess capacity of stakeholder assets, businesses and network
|  | Post Endline (2) Feedback with the community. | Meeting space provided by community | Reports, plan, community attendance sheets, meeting minutes, partners | Community continues to show interest in the project
Legal due-diligence
Focus group trainings
Develop long term plan with stakeholders
5.5 | CC Renewals | Dealing with expired paper and also re-energizing community. Renewing community commitment and transparency. More endline feedback | Good SC usage and SE operations | Reporting
5.6 | New SE Investment (back to Phase 2) | Targeting new SEs within the community as in Phase 2 | Good SC usage and SE operations | Reporting

## Schedule
|  |  | 1 |  |  | 2 |  |  | 3 |  |  | 4 |  |  | 1 |  |  | 2 |  |  | 3 |  |  | 4
Phases | # | Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Phase1 | 1.1 | Pre-Baseline
Setup | 1.2 | Baseline
| 1.4 | Post-Baseline
| 1.5 | Pre-Phase 2 test
Phase 2 | 2.1 | Pre-investment
Social Enterprise (SE) Development | 2.2 | Social Enterprise Investment
| 2.2 | Social Enterprise Capacity building
| 2.3 | Pre-Phase 3 test
Phase 3 | 3.1 | Pre-Pilot
CC Pilot | 3.2 | Pilot-Launch
| 3.3 | Post-Pilot
| 3.4 | Pre-Phase 4 test
Phase 4 | 4.1 | Pre-Launch
CC Launch | 4.2 | Launch
| 4.3 | Post-Launch
| 4.4 | Pre-Phase 5 test
Phase 5 | 5.1 | Quarterly Updates
Long term support (recurring yearly) | 5.2 | Pre-Endline
| 5.3 | Endline
| 5.4 | Post-Endline
| 5.5 | CC Renewals
| 5.6 | New SE Investment (back to Phase 2)

## Budget
Phases | # | Activity |  | Item | Unit | Cost | Number | Total
Phase1 | 1.1 | Pre-Baseline | CC | Stakeholder and Community Meetings | meetings | 50 | 4 | 200 | Per community groups identified
Setup | 1.2 | Baseline
| 1.4 | Post-Baseline | CC | Financial - Quotations and Audits | one audit | 300 | 1 | 300
| 1.5 | Pre-Phase 2 test | CC | Survey | per respondent | 0.5 | 1000 | 500
Phase 2 | 2.1 | Pre-investment
Social Enterprise (SE) Development | 2.2 | Social Enterprise Investment | CC | Stakeholder and Community Meetings | meetings | 50 | 4 | 200
| 2.2 | Social Enterprise Capacity building | CC | Legal (contracts) | one contract | 300 | 1 | 300
| 2.3 | Pre-Phase 3 test | CC | Quotations and professional planning | one plan | 300 | 1 | 300
|  |  | CC | Stakeholder and Community Meetings | meetings | 50 | 4 | 200
|  |  | Private | Investment | Business | 15000 | 1 | 15000 | Equipment, staff, salaries
|  |  | CC/Private | Managment consulting - Business Admin and systems | monthly | 600 | 3 | 1800
|  |  | GWC/CC | Community Trainings - Community/Enviromental Consulting | Trainings | 80 | 4 | 320
|  |  | CC | Marketing Materials / Branding / Events | monthly | 100 | 6 | 600
Phase 3 | 3.1 | Pre-Pilot
CC Pilot | 3.2 | Pilot-Launch | CC | Stakeholder and Community Meetings | meetings | 50 | 4 | 200
| 3.3 | Post-Pilot | CC | Paper Community-Currency Printing/preperation | bill | 0.1 | 5000 | 500
| 3.4 | Pre-Phase 4 test |  | Stakeholder and Community Meetings | meetings | 50 | 4 | 200
Phase 4 | 4.1 | Pre-Launch | CC
CC Launch | 4.2 | Launch | CC | Stakeholder and Community Meetings | meetings | 50 | 4 | 200
| 4.3 | Post-Launch | CC | Paper Community-Currency Printing/preperation | bill | 0.1 | 15000 | 1500
| 4.4 | Pre-Phase 5 test
Phase 5 | 5.1 | Quarterly Updates | CC | Stakeholder and Community Meetings | meetings | 50 | 4 | 200
Long term support (recurring yearly) | 5.2 | Pre-Endline |  | Financial - Quotations and Audits | one audit | 300 | 1 | 300
| 5.3 | Endline | CC | Stakeholder and Community Meetings | meetings | 50 | 4 | 200
| 5.4 | Post-Endline | CC | Survey | per respondent | 0.5 | 1000 | 500
| 5.5 | CC Renewals | CC | Stakeholder and Community Meetings | meetings | 50 | 4 | 200
| 5.6 | New SE Investment | CC | Stakeholder and Community Meetings | meetings | 50 | 4 | 200
[7 empty] | TOTAL | 23920
|  |  |  | Market and Currency Development | Unit | Cost | Number | Total
|  |  |  | Stakeholder and Community Meetings | meetings | 50 | 40 | 2000
|  |  |  | Survey | per respondent | 0.5 | 2000 | 1000
|  |  |  | Paper Community-Currency Printing/preperation | bill | 0.1 | 20000 | 2000
|  |  |  | Financial - Quotations and Audits | one audit | 300 | 2 | 600
|  |  |  | Legal (contracts) | - | 1000 | 1 | 1000
|  |  |  | Quotations and professional planning | one plan | 300 | 1 | 300
|  |  |  | Managment consulting - Business Admin and systems | monthly | 600 | 3 | 1800
|  |  |  | Community Trainings - Community/Enviromental Consulting | Trainings | 80 | 4 | 320
|  |  |  | Marketing Materials / Branding / Events | monthly | 100 | 6 | 600
9620
|  |  |  | SE Development | Unit | Cost | Number | Total
|  |  |  | Investment - Social Enterprise Development | Business | 15000 | 1 | 15000
[7 empty] | TOTAL Activities | 24620
|  |  |  | Regional Office | Unit | Cost | # | TOTAL Yearly
|  |  |  | Office Rent | Monthly | 450 | 12 | 5400
|  |  |  | Transport | Monthly | 200 | 12 | 2400
|  |  |  | Communications | Monthly | 250 | 12 | 3000
|  |  |  | Coordinators | Monthly | 800 | 12 | 9600
|  |  |  | Assistant Coordinators | Monthly | 350 | 12 | 4200
|  |  |  | Regional M&E Manager (per region) | Monthly | 800 | 12 | 9600
|  |  |  | Program Implementation Misc. | Monthly | 100 | 12 | 1200
|  |  |  | Staff Training | Quarterly | 200 | 4 | 800
[7 empty] | TOTAL Yearly | 36200
[7 empty] | Monthly | 3016.6667
|  |  |  | Country Office | Unit | Cost | # | TOTAL
|  |  |  | Rent | Monthly | 1000 | 12 | 12000
|  |  |  | M&E Director | Monthly | 800 | 12 | 9600
|  |  |  | Country Director | Monthly | 1000 | 12 | 12000
|  |  |  | Grant Writer | Monthly | 800 | 12 | 9600
|  |  |  | IT Director | Monthly | 800 | 12 | 9600
[7 empty] | TOTAL | 52800
[7 empty] | Monthly | 4400